## 00_Cover
Nibras (People · My · Team)
UAT / QA Checklist & Sign-off Workbook
Document version: v0.1
Release date: 2026-09-20
How to use
1) Fill 01_Environment with the customer URLs and test accounts. 2) Execute sheets A → B → C → D top to bottom. 3) Set Result to PASS / FAIL / BLOCKED / N/A from the dropdown. 4) Attach evidence (screenshot ID or ticket) in Evidence / notes. 5) Complete 99_SignOff and obtain customer signature or email ACK.
Source of cases: docs/QA-MANUAL-PEOPLE-MY-TEAM.md (customer-facing rewrite)
Related ops (internal): docs/nibras/GOFSCO-ONBOARDING-RUNBOOK.md

## 01_Environment
Item | Value (fill in) | Notes
Frontend URL |  | Customer production or UAT URL
Backend / API base |  | If distinct from FE proxy
Brand / instance | nibras
HR admin test user |  | People access
Employee test user |  | My access — emp_<no>
Manager test user |  | Team access — manages employee above
Browser |  | Chrome / Edge / Safari + version
UAT start date
UAT end date
Build / release tag |  | Match deployed version

## A_People
ID | Case | Goal | Steps | Expected / PASS criteria | Preconditions | Result | Tester | Date | Evidence / notes
A1 | Add employee | HR creates employee with position, salary, Kuwaitization, rotation, manager | People → Employees → Add; fill required fields; Save | Row appears; detail GET persists all fields | At least one Position exists
A2 | Edit / deactivate / reactivate | Lifecycle controls work | Edit salary/position; Deactivate; Reactivate | is_active and fields match after each step | Employee from A1
A3 | Positions CRUD | Create and edit Position | People → Positions → Add → Edit → Save | Edits persist
A4 | Compliance rules | Authoritative rule with schema | Policies/Config → Compliance Rules → Add authoritative rule | Rule listed with is_authoritative and provenance
A5 | Leave policy create | Policy with category/tags | People → Policies → Add Policy; set category/tags; Save | Filter by category/tag works
A6 | Leave policy scope | Kuwaiti 42 / expat 30 / rotation scope | Create scoped policies; Save | Scope fields persist on detail
A7 | Policy versioning | Fork / version history | New Version/Fork; open Version History | ≥2 versions; snapshot includes scope fields | Active policy exists
A8 | Propagate entitlements | Dry-run then apply for year | Policy detail → Propagate | Entitlements only for eligible; idempotent re-run | Scoped policies + employees
A9 | Leave entitlements/records | HR lists and posts leave | People → Leave; add LeaveRecord | Record listed
A10 | Benefits | Benefit types + assign | Config → Benefit Types; assign to employee | Types and benefits listed
A11 | Compensation ledger verify | Components, plan, verify line | Config components/plan; verify employee ledger line | Verify returns success
A12 | Loans | Issue loan + installments | People → Loans → add | Loan + installments listed
A13 | Attendance | Record + permission | People → Attendance | Rows persist | Skip if hidden from go-live nav
A14 | Certifications | Add certification | People → Certifications | Shows on employee
A15 | Rotation schedules | Define pattern | People → Rotation | Schedule listed | Skip if hidden from go-live nav
A16 | Payroll lifecycle | Compute → validate → commit → WPS | People → Payroll full cycle | Each step succeeds; WPS downloadable | Verified ledger; salary production-safe
A17 | EOSI + timeline | Compute EOSI; view timeline | Employee → EOSI; Timeline | Numeric EOSI; events listed

## B_My
ID | Case | Goal | Steps | Expected / PASS criteria | Preconditions | Result | Tester | Date | Evidence / notes
B1 | My profile | Employee sees own profile | My → Dashboard | Own profile rendered | User linked to employee
B2 | Leave balance | Entitled/carried/used/pending/remaining | My → My Leave | Balance widget shows five figures | Entitlements propagated
B3 | Request leave | Submit leave request | My Leave → Request Leave → submit | Confirmation; appears in My Requests | Manager assigned
B4 | Track requests | Status + history | My → My Requests → open detail | Status visible | Request from B3
B5 | Profile change request | Submit personal-data change | Dashboard → Request Profile Change | Request created and routable
B6 | My loans | See own loans | Dashboard loans section | Own loans listed | Loan exists for employee

## C_Team
ID | Case | Goal | Steps | Expected / PASS criteria | Preconditions | Result | Tester | Date | Evidence / notes
C1 | Approvals inbox | Manager sees actionable items | Team → Approvals Inbox | Submitted/in_review items appear | Manager hierarchy set
C2 | Approve | Approve leave | Open request → Approve | Status approved; employee balance updates | Item from B3
C3 | Reject | Reject with reason | Open → Reject → reason | Rejected with reason stored
C4 | Send back | Return for revision | Open → Send Back → note | Requestor can edit/resubmit
C5 | Multi-step chain | Two-step approval | Approve as step-1 then step-2 | Final only after last step | Workflow configured

## D_CrossApp
ID | Case | Goal | Steps | Expected / PASS criteria | Preconditions | Result | Tester | Date | Evidence / notes
D1 | End-to-end leave loop | My → Team → My → People | 1) Employee requests leave 2) Manager approves 3) Employee sees approved + balance 4) HR sees LeaveRecord | No silent data drop across apps | Two users: employee + manager

## E_GOFSCO_Matrix
# | Requirement | Where | Verify via | Result | Notes
1 | Compliance rule engine (authoritative, versioned) | People ComplianceRule | A4
2 | Kuwaitization leave (42 vs 30) | LeavePolicy scope | A6 + A8
3 | Rotation leave scoping | LeavePolicy rotations | A6 + A8
4 | Payroll lifecycle → WPS | PayrollRun | A16
5 | EOSI indemnity | Employee EOSI | A17
6 | Benefits & compensation categories | BenefitType / Comp | A10 + A11
7 | HR Reporting module | Not built | N/A roadmap | N/A | Acknowledged gap
8 | Full HR module registry | Not built | N/A roadmap | N/A | Acknowledged gap

## 99_SignOff
UAT Sign-off
Area | PASS? | Comments
Part A — People
Part B — My
Part C — Team
Part D — Cross-app journey
GOFSCO matrix 1–6
Known gaps 7–8 acknowledged
Overall recommendation | READY / READY WITH EXCEPTIONS / NOT READY
Vendor tester name
Vendor tester date
Customer UAT lead name
Customer UAT lead date
Customer signature / email ACK reference
By signing, the customer confirms the executed cases reflect acceptance of People / My / Team for the stated release, subject to any FAIL/BLOCKED items listed as agreed exceptions.