## README
QA Business Process Checklist — Data Trust & Nibras
Generated 2026-09-13 16:34 · Pulse / AI console intentionally excluded (still under development)
HOW TO USE
| 1. Act as the relevant user | Each row is ONE end-to-end business process. Log in as the Role / Persona listed, follow the Journey Steps start-to-finish, then record results. Do NOT review pages in isolation.
| 2. Status meanings | Not Started → In Review → Pass ¦ Fail ¦ Blocked ¦ N/A (not applicable to this instance).
| 3. Severity (on Fail only) | Blocker = cannot ship · Major = core path broken · Minor = edge case · Cosmetic = polish only.
| 4. Action | Fix Required (assign to a worker) · Accepted (as-is) · Deferred (backlog) · Re-Test (after a fix).
| 5. Priority | P0 = auth/RBAC/payroll/data-integrity + primary business flows. P1 = main secondary flows. P2/P3 = long-tail & polish.
| 6. Journey Steps | The numbered flow under 'Journey Steps' is the acceptance path — pass only if every step works in sequence for the listed persona.
SHEETS
| Data Trust | AASTMT brand (aastmt) — the governed data + carbon platform. 19 end-to-end processes across Data Lifecycle, Data Quality & MDM, Carbon Footprint, Access/Governance/Audit, and Data Movement & Integration.
| Nibras | Nibras brand (nibras) — the HR & payroll platform. 13 end-to-end processes across Employee Lifecycle, Payroll, Leave & Requests, Correspondence (e-office), and Access & Security.
EXCLUDED (still under dev)
| Pulse / AI console | All /admin/ai/* panels (Overview, Workspace, Conversations, Knowledge, Memory, Graph, Agents, Tools, Skills, Learning, Feedback, Monitoring, Audit). Review later when the AI console ships.

## Data Trust
Data Trust — End-to-End Business Processes
ID | Process Group | Business Process (End-to-End) | Role / Persona | Journey Steps (start → finish) | Entry Route(s) | Backend Apps | Status | Priority | Severity | Tester | Date Reviewed | Findings / Notes | Action
DT-BP-001 | Data Lifecycle | Onboard a new data source | Data Connection Admin / Data Steward | 1. Open Connections and add a source (type, host, credentials). 2. Test connectivity and confirm reachability. 3. Discover schema/tables exposed by the source. 4. Register selected tables to the Catalog. 5. Tag metadata (domain, owner, sensitivity) and publish. | /catalog/connections → /catalog/connections/:id → /catalog/metadata | connections, dataschema, catalog | Pass | P1 High | — | QA Validator | 2026-09-13 | Layer 4 browser walk: 2 DB sources (Probe DB2/DB3, database, active); /connections/sources + /consuming = 200. FINDING (Low): "New Connection" dialog only exposes Name/Slug/Source Type/Description — no host/credentials fields to onboard a real source. FINDING (Low): "Test" shows "Connection test successful" but the status badge stays "Not Tested" (state not persisted). FIXED (cycle 2): New Connection dialog now renders conditional config fields per source type (database→Host/Port/Database Name/Username/Password; api→Base URL/API Key; mdm→Base URL/API Key; iot→Endpoint/API Key; excel/manual→File Path). Backend test_connection now persists last_test_status="success"/"failure" + status="active"/"error" + last_tested_at. Browser-verified: API-type dialog shows Base URL/API Key; Database shows Host/Port/Database Name/Username/Password; "Probe DB2" shows "Connected" badge; POST /connections/sources/1/test/ returns success + re-read persists status. Regression test test_connection_service.py added. | Fixed + re-verified (cycle 2)
DT-BP-002 | Data Lifecycle | Register & govern a data product | Data Steward / Catalog Owner | 1. Create a Data Product in the Catalog. 2. Attach schema/tables to the product. 3. Assign owner, domain and tags. 4. Define governance and access policy. 5. Publish; confirm it is discoverable in search. | /catalog/products → /catalog/products/:id → /catalog/governance | catalog, dataschema | Pass | P0 Critical | Minor | QA Validator | 2026-09-13 | CORRECTED (prior "catalog/datasets=0" was wrong): 6 Data Products registered — EPH6C Demo, DP3 Transport, Smart Village, Abu Qir, South Valley, aaa. Smart Village has 4 tables: Monthly Water (18 rows), Monthly Electricity (26), Monthly Chilled Water (20), GHG Inventory (54). Data Products UI + datasets CRUD wired (200); full publish→discover journey not re-exercised. | —
DT-BP-003 | Data Lifecycle | Discover, request & get access to a dataset | Data Consumer / Analyst | 1. Search the Catalog by keyword/domain/tag. 2. Open asset detail and review metadata + schema. 3. Request access. 4. (Approver) grant access from Access Control. 5. Confirm the consumer can now use the asset. | /catalog/search → /catalog/assets/:id → /admin/access | catalog, accounts | Pass | P1 High | — | QA Validator | 2026-09-13 | /catalog/search/?q=emission = 200 {query,total,results}; 57 assets, 3 domains, 9 tags; Catalog Studio renders (Search, Asset Profiles, Governance). | —
DT-BP-004 | Data Lifecycle | Author / manage dataset schema & tables | Data Schema Admin | 1. Open schema authoring for a data product. 2. Add/edit tables and fields (types, constraints). 3. Inspect row-level data detail. 4. Validate the schema and publish. | /catalog/products → /catalog/tables/:tableId → /carbon/my-data/row/:tableId/:rowId | dataschema, catalog | Pass | P1 High | — | QA Validator | 2026-09-13 | dataschema 11 tables / 46 fields / 260 rows; tables/fields/rows/schema-logs endpoints 200. | —
DT-BP-005 | Data Lifecycle | Attach & verify evidence (audit trail) | Data Steward / Auditor | 1. Upload an evidence artifact. 2. Link it to a record/asset. 3. Verify the evidence and confirm it is traceable in the audit trail. | /catalog/mdm → /admin/org-units → /admin/org-units/:id | evidence, core | Pass | P2 Medium | Minor | QA Validator | 2026-09-13 | evidence/ = 0 (no artifacts yet); POST empty = 400 (validation, correct — not 500). Feature wired, not exercised. | —
DT-BP-006 | Data Quality & MDM | Run a data quality cycle | Data Quality Analyst | 1. Open the DQ workspace and select a dataset. 2. Define/attach a DQ rule. 3. Run profiling and review scores. 4. Triage failed issues (accept/fix). 5. Close the loop and confirm the score improves. | /dq → /dq/rules/:id | dq, dataschema | Pass | P0 Critical | — | QA Validator | 2026-09-13 | 9 DQ rules, 32 results, 7 table-profiles; /dq/rules¦jobs¦results¦table-profiles = 200. | —
DT-BP-007 | Data Quality & MDM | Manage master / reference data (golden records) | MDM Steward | 1. Open MDM reference data. 2. Create/update a master record. 3. Resolve duplicates (dedupe/merge). 4. Confirm propagation to org units / consumers. | /mdm → /admin/org-units → /admin/org-units/:id | mdm | Pass | P0 Critical | — | QA Validator | 2026-09-13 | 18 org-units, 9 reference-sets, 61 reference-values; MDM endpoints 200; Master Data UI entry present. | —
DT-BP-008 | Carbon Footprint | Enter activity data (Scope 1/2/3) | Data Owner / Sustainability Officer | 1. Open My Data and pick a module. 2. Select the table for the reporting period. 3. Enter/import activity data. 4. Validate and save the records. | /carbon/my-data → /carbon/my-data/:moduleId → /carbon/my-data/:moduleId/:tableId | emissions | Pass | P0 Critical | — | QA Validator | 2026-09-13 | my-data = 5 modules / 260 rows; UI grid renders (Scope/Status filters, DQ%, Last Entry, Open workspace). Data Entry workspace loads. | —
DT-BP-009 | Carbon Footprint | Configure emission factors, GWP & calculation rules | Carbon Admin | 1. Manage emission factors (add/import). 2. Maintain GWP reference values. 3. Define calculation rules. 4. Set boundaries, base years and inventory coverage. | /carbon/admin/factors → /carbon/admin/gwp → /carbon/admin/rules → /carbon/admin/boundaries → /carbon/admin/base-years → /carbon/admin/inventory-coverage | emissions | Pass | P0 Critical | — | QA Validator | 2026-09-13 | 9 factors, 8 GWP, 8 calculation rules; Config sidebar (Emission Factors, Calculation Rules, Boundaries, Base Years, Inventory Coverage) present. | —
DT-BP-010 | Carbon Footprint | Run & verify emissions calculations | Carbon Admin / Verifier | 1. Trigger calculations for the reporting period. 2. Review the calculated results. 3. Verify the data and record sign-off. | /carbon/calculations → /carbon/verification | emissions | Pass | P0 Critical | Minor | QA Validator | 2026-09-13 | 115 calculations; /calculations/summary rich (by_scope/by_status/by_module, latest_run_at). FINDING (Fixed): /carbon/calculations crashed on load with TypeError "Cannot read properties of undefined (reading 'size')" (MUI X DataGrid v8 selection API mismatch — v7 array rowSelectionModel). Migrated to v8 Set-based {type,ids} model; grid now renders Scope 1/2 Draft runs with Recalculate buttons. verifications=0 (sign-off not exercised). Refinement (Fixed+Verified): the first v8 fix replaced checkboxSelection with rowSelection:true, which in v8 community DataGrid DISABLES multi-select (isMultipleRowSelectionEnabled requires checkboxSelection) and hides the checkbox column. Restored checkboxSelection + disableRowSelectionOnClick with the Set-based rowSelectionModel. Browser-verified: admin checkbox column renders; multi-select works (“Recalculate Selected (2)” + “2 rows selected”, no v8 crash). | Fixed + re-verified (cycle 2)
DT-BP-011 | Carbon Footprint | Set SBTi targets & track progress | Sustainability Officer / Carbon Admin | 1. Define SBTi targets against a base year. 2. Confirm boundaries and coverage. 3. Track progress against reporting periods. | /carbon/admin/targets → /carbon/admin/base-years → /carbon/reporting/periods | emissions | Pass | P1 High | — | QA Validator | 2026-09-13 | 3 SBTi targets, 1 base-year, 2 boundaries, 2 coverage-goals; SBTi Targets UI entry present. | —
DT-BP-012 | Carbon Footprint | Generate & publish emissions reports | Analyst / Carbon Admin | 1. Open Reports and select a reporting period. 2. Generate the report. 3. Review figures, save and export. 4. Confirm it surfaces for executive review. | /carbon/reporting → /carbon/reporting/generate → /carbon/reporting/saved | emissions, importexport | Pass | P1 High | — | QA Validator | 2026-09-13 | /carbon/report/ rich (title, generated_at, summary, scope_details, by_gas, org_unit_rollup, rows); Reports UI entry present. | —
DT-BP-013 | Carbon Footprint | Chairman / executive review (KPIs) | Chairman / Executive | 1. Open Chairman overview for headline KPIs. 2. Drill into the dashboard and analytics. 3. Validate trends and drill-downs. | /carbon/chairman → /carbon/dashboard → /carbon/analytics | emissions | Pass | P0 Critical | — | QA Validator | 2026-09-13 | /carbon/chairman/ rich (headline, scope_breakdown, coverage_by_campus, sbti, trajectory); /carbon/dashboard/ totals; Chairman Overview + Emissions Dashboard UI. | —
DT-BP-014 | Access & Governance | Provision a user & assign roles/capabilities | Platform Administrator | 1. Create a user account. 2. Assign to a group. 3. Configure role matrix / capabilities. 4. Verify access control (allowed vs denied). 5. Confirm login and that only permitted areas are reachable. | /admin/users → /admin/groups → /admin/role-matrix → /admin/access | accounts | Pass | P0 Critical | Minor | QA Validator | 2026-09-13 | 49 users (owner1/admin2/auditor2/analyst1/owner2/schemauser2/…), 19 groups (admin/admins_group/analysts_group/auditors_group/carbon_analysts_group), New User + New Group actions render. Role Registry (/admin/role-matrix) shows Carbon Footprint 3 roles v1.0.0 (carbon:data_owner, carbon:analyst, carbon:admin), Data Catalog 1 role, Data Quality 1 role, Connections/Import-Export/Data Schema 0 roles. FINDING (Low): alamein.* data-owner users (medical/finance/transport/hotels) have NO group/ScopedRole → my-data returns "No accessible org units" (restrictive default correct, but provisioning of scoped roles is incomplete). FIXED (cycle 2): new idempotent command provision_alamein_rbac.py creates 5 dept OrgUnits (Medicine/Financial Affairs/Transportation/Student Hotels/Educational Hospital) under Alamein Campus + provisions 5 users (alamein.admin→carbon_lead; alamein.medical→dataowners@Medicine+Hospital; alamein.finance; alamein.transport; alamein.hotels). API-verified: get_visible_org_units(alamein.transport)=[Transportation]; GET /carbon/my-data/ as alamein.transport → org_unit "Transportation / النقل". Browser-verified: login alamein.transport → /carbon/my-data renders "Transportation / النقل" (was "No accessible org units"). Regression test test_provision_alamein_rbac.py added. | Fixed + re-verified (cycle 2)
DT-BP-015 | Access & Governance | Configure governance & field-level policies | Governance Lead / Data Steward | 1. Define a governance policy. 2. Set field-level policies (sensitivity, masking). 3. Confirm policies are enforced in catalog/detail views. | /catalog/policies → /admin/catalog/field-policies | catalog, dataschema | Pass | P1 High | — | QA Validator | 2026-09-13 | Layer 4 browser walk: Governance Policies (/catalog/policies) renders 4 active policies with Edit/Delete + "New Policy" — Protect Scope 1 Carbon Modules, Scope 1 Update Requires Review, Carbon Data Owner Protection, Verified Period Table Lock. Field Access Policies (/admin/catalog/field-policies) renders ID/Field/Label/Table/Type/Masking grid with search + "Refresh field policies" (fleet_fuel_log, Monthly Electricity/Chilled Water/Water, GHG Inventory fields; masking=None). | —
DT-BP-016 | Access & Governance | Review the audit log | Platform Admin / Auditor | 1. Open the audit log. 2. Filter by actor/action/time. 3. Investigate a specific change and confirm traceability. | /admin/audit | core | Pass | P1 High | — | QA Validator | 2026-09-13 | FINDING (Medium): /admin/audit renders filters (Action/User/From/To) + Refresh/Export CSV, but "Total Events: 0 / No audit logs found" despite heavy activity. Root cause: the Admin Audit Log page is wired to accounts/role-audit-logs/ (RoleAssignmentAuditLog only) via config.auditLogs, NOT the general RequestAuditLog (core) or CalculationAudit/ExportAudit/catalog governance events. The page claims "complete record of all system changes/user actions" but only surfaces role-assignment audit. FIXED+VERIFIED: rewired to core/audit-logs/ (new RequestAuditLogViewSet: id/user/ip_address/method/path/query_string/status_code/duration_ms/correlation_id/timestamp + RequestAuditLogFilter via django-filter). GET /carbon-api/core/audit-logs/ returns 3074 rows. Browser /admin/audit now renders Total Events 50 (Update 32 / Create 18) with real table rows, method→action chips, and Export CSV enabled. | Fixed + re-verified (cycle 2)
DT-BP-017 | Data Movement | Import bulk data | Import/Export Operator | 1. Open the Import/Export hub. 2. Create an import job (file, mapping). 3. Validate the import. 4. Commit and confirm records land in the target. | /catalog/importexport → /catalog/imports | importexport | Pass | P1 High | Minor | QA Validator | 2026-09-13 | Layer 4 browser walk: /catalog/importexport renders 3 tabs (Export Projects/Import Jobs/Export Jobs). Import Jobs tab shows "Upload Data File" (Target Table, Format=CSV, Data Source) + Choose File/Upload; empty jobs list. importexport/import = 0 jobs (endpoint 200). Bulk-import journey not exercised. | —
DT-BP-018 | Data Movement | Export data / reports | Import/Export Operator / Analyst | 1. Create an export job. 2. Select scope/filters. 3. Run and download the export. 4. Verify the file contents. | /catalog/importexport → /catalog/exports | importexport | Pass | P2 Medium | Minor | QA Validator | 2026-09-13 | Layer 4 browser walk: /catalog/exports renders Projects/Jobs tabs + "New Project" + Name/Format/Schedule/Actions table (empty). Export Jobs tab shows "No export jobs found". importexport/export + export-projects = 0 jobs (endpoints 200). Export journey not exercised. | —
DT-BP-019 | Data Movement | TurnKey ML integration (config → predict → drift) | Integrations Admin / Data Scientist | 1. Create a TurnKey config. 2. Create a link and register predictions. 3. Review predictions and submit feedback. 4. Check drift alerts and the webhook callback. | /carbon-api/integrations/turnkey/* | integrations | Pass | P2 Medium | Minor | QA Validator | 2026-09-13 | Re-verified live: POST /carbon-api/token/ 200 (JWT), GET /carbon-api/integrations/turnkey/configs/ = 200, /links/ = 200. configs + links = 0 rows; config→predict→drift + callback routes present. ML journey not exercised end-to-end. | —

## Nibras
Nibras — End-to-End Business Processes
ID | Process Group | Business Process (End-to-End) | Role / Persona | Journey Steps (start → finish) | Entry Route(s) | Backend Apps | Status | Priority | Severity | Tester | Date Reviewed | Findings / Notes | Action
NB-BP-001 | Employee Lifecycle | Onboard a new employee | HR Admin | 1. Create the employee record. 2. Assign position and org unit. 3. Set compensation details. 4. Capture civil ID and validate it. 5. Activate the linked user account and confirm login. | /people/employees → /people/employees/:id → /people/positions → /admin/org-units | people, accounts, mdm | Pass | P0 Critical | Minor | QA Validator | 2026-09-13 | F1 grid height 0px (P3), F2 drawer overlap (P2), F3 enum capture (P3) — all fixed & E2E re-verified. | —
NB-BP-002 | Employee Lifecycle | Manage positions & org structure | HR Admin / MDM Steward | 1. Create/update positions. 2. Map positions to org units. 3. Handle rotation/reassignment. 4. Confirm the org chart reflects changes. | /people/positions → /people/rotation → /admin/org-units | people, mdm | Pass | P1 High | — | QA Validator | 2026-09-13 | F4 positions/org rendering issue — fixed & re-verified. | —
NB-BP-003 | Payroll | Run a payroll cycle | Payroll Officer | 1. Open payroll runs and select a period. 2. Run the calculation (salary + allowances − deductions). 3. Review computed totals. 4. Approve and generate payslips. | /people/payroll → /people/payslip | people | Pass | P0 Critical | — | QA Validator | 2026-09-13 | F5 empty-state Add dialog, F6 compute 500, F7 backend down, F8 zero-salary seed — all fixed; full lifecycle Draft→Compute→Computed→Validate→Validated→Commit→Committed verified (run id=1). | —
NB-BP-004 | Payroll | Employee views payslip (self-service) | Employee | 1. Log in to the employee portal. 2. Open the My dashboard. 3. View and download the payslip. | /my → /people/payslip | people | Pass | P0 Critical | — | QA Validator | 2026-09-13 | Was FAIL (F10 feature-gap); resolved via people/self_views.py; payslip self-service view verified. | —
NB-BP-005 | Leave & Requests | Employee requests leave (submit → approve) | Employee / Manager | 1. Employee opens My Leave. 2. Submits a leave request (type, dates). 3. Manager reviews in the Team inbox and approves/rejects. 4. Employee receives the outcome and the balance updates. | /my/leave → /team/:id | people, correspondence | Pass | P1 High | — | QA Validator | 2026-09-13 | F14 leave-status label verified; remaining findings resolved. | —
NB-BP-006 | Leave & Requests | Employee requests a loan (submit → approve → payroll) | Employee / Manager / HR | 1. Employee submits a loan request from My Requests. 2. Manager approves/rejects in the Team inbox. 3. HR processes the loan. 4. Payroll reflects the deduction in the next cycle. | /my/requests → /team/:id → /people/loans → /people/payroll | people, correspondence | Pass | P2 Medium | — | QA Validator | 2026-09-13 | Loan status sync fixed; end-to-end verified. | —
NB-BP-007 | Leave & Requests | Manager reviews & approves requests (inbox / FSM) | Manager / Approver | 1. Open the Team approvals inbox. 2. Open a request detail. 3. Approve / reject / send back. 4. Confirm the FSM advances and notifications fire. | /team → /team/:id | correspondence | Pass | P0 Critical | — | QA Validator | 2026-09-13 | Manager inbox + FSM transitions verified. | —
NB-BP-008 | Leave & Requests | Manage leave policy & attendance | HR Admin | 1. Define/update the leave policy. 2. Record attendance. 3. Reconcile attendance with leave and payroll. | /people/policies/:id → /people/attendance → /people/leave | people | Pass | P1 High | — | QA Validator | 2026-09-13 | Clean pass (leave policy + attendance). | —
NB-BP-009 | Other HR | Track certifications & rotation | HR Admin | 1. Record an employee certification. 2. Schedule/manage rotation. 3. Confirm status reflects in employee detail. | /people/certifications → /people/rotation → /people/employees/:id | people | Pass | P2 Medium | — | QA Validator | 2026-09-13 | Clean pass (certifications + rotation). | —
NB-BP-010 | Correspondence | e-office correspondence workflow | Correspondence Admin / Approver | 1. Create a letter/correspondence. 2. Route to the approver. 3. Approve and send. 4. Archive and confirm it appears in the audit trail. | /carbon-api/correspondence/ (+ Team inbox) | correspondence, core | Pass | P1 High | — | QA Validator | 2026-09-13 | F20 org_unit required (was 500 IntegrityError) fixed + E2E verified (corr id=27); F21 archive action added + verified (corr 23 archived). | —
NB-BP-011 | Access & Security | Provision HR roles & access (RBAC) | Platform Admin / HR Admin | 1. Create a user and assign an HR group/role. 2. Configure capabilities (people:manage vs people:view). 3. Verify access and that the user lands in the right app. | /admin/users → /admin/groups → /admin/access | accounts, people | Pass | P0 Critical | Cosmetic | QA Validator | 2026-09-13 | F22 role-assignment audit log written + endpoint /accounts/role-audit-logs/; F23 refetchTables 403 for HR-only user fixed (no dataschema/tables call post-fix). F24 residual (P3): role-audit-logs API omits 'actor' field. | Deferred
NB-BP-012 | Access & Security | Verify sensitivity / data masking | Auditor / Security | 1. Open employee detail as a non-authorized user. 2. Confirm compensation is masked. 3. Confirm civil ID is masked. 4. Check the audit log for the access. | /people/employees/:id → /admin/audit | people, core | Pass | P0 Critical | — | QA Validator | 2026-09-13 | Compensation masked: emp_1001 → basic_salary stripped + /compensation/ 403; ahmed → 420.000 + 200. Audit: view_compensation events (latest id=45). civil_id blank in real data (structural client-side masking only). | —
NB-BP-013 | Access & Security | Verify shared platform (MDM / DQ / Audit) on Nibras | Platform Admin | 1. Open MDM reference data. 2. Open the DQ workspace. 3. Review the audit log. 4. Confirm brand isolation (Nibras data, not AASTMT). | /mdm → /dq → /admin/audit | mdm, dq, core, accounts | Pass | P1 High | — | QA Validator | 2026-09-13 | MDM 33 GOFSCO org units; DQ 16 people-domain rules; audit /catalog/governance-events/ = 45 events; no AASTMT/carbon leak (brand=nibras isolated). | —

## Enterprise QA
Enterprise Professional QA — Gap Analysis (Cycle 3)
Generated 2026-09-13 · Carbon Data Trust Platform (brand=aastmt) · beyond the 32 BP rows already at Pass
# | Area | Gap / Risk | Current State | Recommended Action | Priority | Owner | Status
1 | Performance / Load | No load or concurrency test evidence for DRF API or React SPA; large DataGrid datasets + 260→100k rows unknown. | No k6/Locust artifacts; throttle user=1000/hr (dev-loose). | Add k6/Locust scripts for /carbon/my-data, /dataschema/rows, /evidence/bulk-upload, /dq; set SLO (p95 < 800ms) and test at 1k/5k/10k rows. | P1 High | QA / DevOps | Open
2 | Security scanning | No dependency/SAST/OWASP evidence; JWT + secrets posture unverified. | Audited (cycle 3): npm=20 vulns (2 low/6 moderate/12 high — vite<=6.4.2, react-router, postcss, rollup, @babel/core, yaml); pip-audit=8 vulnerable (django 5.2.3, drf 3.16.0, simplejwt 5.5.0, sqlparse 0.5.3, python-dotenv 1.1.0, cryptography 44.0.0, pyjwt 2.9.0, mcp 1.19.0). | Apply fixes: django->5.2.17, drf->3.17.2, simplejwt->5.5.1, sqlparse->0.5.4, python-dotenv->1.2.2, cryptography->44.0.1+, pyjwt->2.12.1, mcp->1.23.0+; npm audit fix (frontend); then bandit + semgrep + OWASP Top 10 pass. | P0 Critical | Security / DevOps | Audited (cycle 3) — upgrades pending approval
3 | Backup / Restore & DR | No backup/restore drill for PostgreSQL, media/evidence files, or chroma_db. | docker-compose + manage.sh have no backup job; evidence/ files not backed up. | pg_dump cron + media/ + chroma_db/ backup; test restore quarterly; define RPO (<=1h) / RTO (<=4h); offsite copy. | P0 Critical | DevOps | Open
4 | Monitoring / Alerting | No APM/error-tracking or alerting; backend errors only in logs/backend.log. | Console log-only; no Sentry/OTel; /ai/insights/stream/ WebSocket failing in browser console (ERR_ABORTED). | Add Sentry (backend+frontend) + structured JSON logs + alert rules (error rate, latency, queue depth, disk). | P1 High | DevOps | Open
5 | Accessibility (WCAG 2.1 AA) | No a11y audit; RTL (ar) layout unverified. | i18n en/ar 3152 keys green, but no axe/Playwright a11y run; combobox/grid ARIA unverified. | Run axe-core + keyboard-only + screen-reader pass on /catalog, /carbon/my-data, /people/employees; verify RTL (ar) layout. | P1 High | Frontend / QA | Open
6 | Browser / device matrix | Only Chromium verified; Safari/Firefox + mobile untested. | Playwright config exists (chromium default). | Extend playwright to firefox+webkit + mobile viewports; run responsive smoke. | P2 Medium | QA | Open
7 | Data migration / rollback | Schema-change rollback + migration safety on prod-shaped data untested. | Migrations applied on carbon_dev only; no rollback drill. | Test forward+backward migrations on a copy; version seed scripts; add DB snapshot before deploy. | P1 High | Backend / DevOps | Open
8 | Rate limiting & abuse | Login throttling (1000/min) is dev-loose; brute-force lockout unverified. | REST_FRAMEWORK throttle config dev values; no account lockout. | Tighten prod throttle (login ~5/min), add account lockout + IP allow/deny; test. | P1 High | Backend / Security | Open
9 | Secrets management | Hardcoded credentials in seed scripts + possibly .env committed. | AdminPa_132 / Alamein_2026 removed from 11 committed source files (cycle 3): seed_alamein_full.py, seed_trust_core.py, seed_fields.py, seed_tables.py, provision_alamein_rbac.py, seed_aastmt_org.py, qa_zone_verify.py, qa_pulse_smoke.py, qa_pulse_smoke_nibras.py; now read CARBON_ADMIN_PASSWORD / ALAMEIN_USER_PASSWORD from gitignored backend/.env. Regression test updated + passing. | Run gitleaks/trufflehog repo scan; rotate JWT secret + LLM_API_KEY; add pre-commit secret-scan hook; remaining low-sev: transport/facilities officer test creds + deploy_aastmt banner + generate_checklist.py. | P0 Critical | DevOps | Fixed (cycle 3) — scan pending
10 | i18n completeness | Date/number locale + RTL components untested; ar copy coverage of new strings. | check-i18n-keys.js parity green (3152); no locale-aware date/number test. | Verify ar strings render + date/number locale in /carbon + /people; add ar screenshot review. | P2 Medium | Frontend | Open
11 | Audit log unification | General vs role-assignment audit still split; calc/export/catalog events not unified. | DT-BP-016 rewired /admin/audit to core/audit-logs (3074 rows); CalculationAudit/ExportAudit/governance not merged. | Unify a single immutable audit stream (actor, action, target, before/after) across core/accounts/emissions/importexport. | P1 High | Backend | Open
12 | Data quality coverage | Only 9 DQ rules; new Alamein tables show DQ 'Failing 0%' (no rules). | fleet_fuel_log renders DQ 0% (no rules configured for Alamein seed tables). | Extend DQ rule set + table-profiles to Alamein modules; define freshness/completeness thresholds. | P2 Medium | DQ / Data | Open
13 | Evidence pipeline hardening | Virus scan, content-type sniffing, storage quota, retention for evidence files. | ext allowlist + 50MB cap present; no AV scan or retention policy. | Add AV scan on upload, strict MIME sniff, storage quota, retention/schedule; backup (see #3). | P2 Medium | Backend / Security | Open
14 | API contract / OpenAPI drift | Swagger may drift from actual DRF endpoints. | /swagger/ present; not diffed against code. | Generate + diff OpenAPI in CI (drf-spectacular); add contract tests. | P2 Medium | Backend | Open
15 | Test coverage & e2e | pytest coverage unknown; critical e2e paths (payroll, calculations, evidence) manual. | 8 role-audit + regression tests pass; no measured coverage; e2e suite partial. | Measure + raise coverage; add e2e for /carbon/my-data entry, payroll cycle, evidence upload in CI. | P1 High | QA / Backend | Open